## Rushmore
Columns from 2011 Workbook
34 | 35 | 36 | 37 | 38 | 39 | 44 | 73 | 74
Water depth / land well drill floor elevation | Spud depth | MTD final wellbore | Unused lengths due to conting'y geol s/tracks | Locator unused length | TVD | Maximum angle in degrees | Mud weight at TD | Max. mud weight
26.5 | 529.5 | 2091 |  |  | 2091 | 1.46 | 10.55 | 10.55
76 | 77 | 78 | 79 | 80 | 81 | 91 | 92 | 93
Coring days | Coring interval | Logging days not at TD | Logging days at TD | Under reaming days | Under reamed interval | Spud date | Dry hole days | Date of end of dry hole period
0 |  | 0 | 0 | 0 | 0 | 2012-05-18 | 27.96 | 2012-06-15
94 | 95 | 96 | 105 | 106 | 108 | 109 | 110 | 111
No. of well suspen-sions | Days on suspen-sion / re-entry ops | Total WELL SITE days | Date of end of well ops | WOW before de-mooring / move-off | Days spent mooring | Days spent de-mooring | WOW during mooring | WOW during de-mooring
0 |  |  |  |  | 1.16 |  | 0
Simian Db PERFORMANCE FIGURES for BG [DHD ex DA] [+/- 2, using 2008-2009 Sidetrack DPR Curves]
Planned = P40 [1627.5m in 19.56days]; this is spud to end pilot hole phase
Actual = P70 [1561m in 28days]; P25 would be 1627.5m in 16.6 days;
SIDETRACK & COMPLETION CANCELLED
S/T Planned = P35 approx. [300m in 6.7days]; this is kick off @ 1807m to end of 8 1/2" x 12 1/4" phase
S/T Actual = PXX [XXXm in XXXdays]; this is drill from XXXXm to end of 8 1/2" x 12 1/4" phase P25 would be 300m in 6.35 days
Note on G5: Kes Evoy: 1.46 @ 570m
Note on H5: Kes Evoy: TD @ 2091m (Pilot Hole)
Note on I5: Kes Evoy: TD @ 2091m (Pilot Hole)
Note on H9: Kes Evoy: SPUD = 11:30 18/05/2012 BHA on surface and next op ready to begin =10:30 15/06/2012
Note on F13: Kes Evoy: On location 16/05/2012 00:00. Mooring from 04:45. End of mooring = 08:30 18/05/2012